## Project Ref
RFT Title |  | LEEXXXY -RFT for the Supply of X for X |  |  |  | Baseline (Ex VAT)
Contracting Authority | [5 empty] | Actual Cost (Ex VAT)
Contracting Authority Contact
Project Lead
OGP Status | TASK DESCRIPTION |  | Owner | Start date | Enter No of days | Estimated Finish Date | STATUS
1 | Preparation Stage |  | (Use dropdown menu) | (Enter start date) | Enter number of days to complete |  | (Use dropdown menu)
1.5 | Pre- Publication
| Prepare draft RFT document |  | EPS |  |  | 0 | Not Started
| Circulate draft documents for approval from stakeholders prior to tender advertisement |  | EPS |  |  | 0 | Not Started
| Documents proofed by Evaluation Team for inserting into OGP RFT template |  | Contracting Authority |  |  | 0 | Not Started
| Customer Sign off |  | Contracting Authority |  |  | 0 | Not Started
2 | Go To Market
2.1 | Conduct GTM Prcress
| Put RFT & Appendices up on E-Tenders to go live |  | EPS |  |  | 0 | Not Started
| Respond to clarifications submitting during advertisement |  | EPS |  |  | 0 | Not Started
| Response/Submissions closing date |  | EPS |  |  | 0 | Not Started
2.2 | Evaluation
| Record the unopened submissions including time & date & open tender responses |  | EPS |  |  | 0 | Not Started
| High Level Overview of solutions offered |  | All |  |  | 0 | Not Started
| Assess in accordance with published selection criteria |  | All |  |  | 0 | Not Started
| Award decision circulated to all EV team - conference or meetup |  | EPS |  |  | 0 | Not Started
2.3 | Contract Approval
| Issue Letters of Notification (Award & Regret) to all bidders |  | EPS |  |  | 0 | Not Started
2.4 | Standstill
| Observe Standstill period (7 /14 Days) |  | EPS |  | N/A | #VALUE! | Not Started
3 | Finalise Arrangement
3.1 | Communication of arrangement
| Issue Letters of Commencement (week commencing) |  | Contracting Authority |  |  | 0 | Not Started
3.2 | Rollout & Mobilisation
| Purchase Orders issued |  | Contracting Authority |  |  | 0 | Not Started
| Final Report : savings |  | Contracting Authority |  |  | 0 | Not Started
TOTAL TIME
0
Formulas:
Baseline (Ex VAT) = SUM([Start date]+[Enter No of days])
A

## Sheet2 (hidden)
Completed
In Progress
Not Started
Delayed
EPS
Contracting Authority
All
N/A
7
14

## Sheet3 (hidden)
DATE
2017-05-11 | 45 | 2017-06-25